## Action Plan 21-23 yr 2
Concordat/HREiR Action plan October 2021-October 2023
Details
| Institution name: | University of Stirling |  |  |  | The institutional audience* for this action plan includes:
| Cohort number: | 4 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff |  | 170 | Cohort of Postdoctoral Research Assistants, Post Doctoral Research Fellows, Research Fellows
| Notes re. template document | Please note that institutions may only amend text in columns J. K & L (those with an orange title row). This is a formal requirement.
[6 empty] | Research and teaching staff |  | 180 | We recognise that Early career academics (teaching & research) can benefit also from the Concordat action plan. For the purpose of the Concordat, our definition of ECR is those who are new post-docs to those transitioning to or establishing independence. There are no rules based on years since PhD or whether the ECR currently holds a permanent/open-ended academic position. An ECR can be someone returning to research from a career break or following time in other roles, with no limits in respect of time spent outside a research environment. There are approx 180 lecturing staff at Stirling. Not all 180 staff will be or identify as an ECR. For this reason, this figure is indicative.
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional). We are using to highlight route for comms or Reg subgroup lead | Progress update (August 2023) | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat. | 1.1. REG to report on Concordat developments at University Research Committee (URC), updates provided via Research Bites blog series, University Concordat & HREiR webpages | Yes | Ongoing | REG chair | Monitor awareness via CEDARS. 43.6% of CEDARS 2021 respondents reported having some understanding in survey conducted in June 2021. Continue to build on this awareness and evaluate progress in CEDARS 2023 |  | Quarterly updates at URC (Aug, Nov, Feb, May) and 3 blogs in Research Bites. HREiR award successfully retained further to 10-year report and action plan submission 28 Jan 2022 with news communicated via Staff Roundup *(University newsletter) 11 April 2022. A blog update on the new 2023-2027 action plan will be released early AY 2023/24 also to highlight the launch of the new researcher guide. | Awareness of Concordat is 34.6% (have some awareness) in 2023 CEDARS. | carry forward - BAU
|  | 1.2. Roadshow raising awareness sessions | No | Annual | REG | as above 1.1 | Faculty Research Committees, IAS committees | REG participation in biannual Research Staff Inductions ( March and October). Dean REP presented at IAS Doctoral Committee in semester two 2021/22, IAS Executive Committee and DP meeting in 2022/23. REG Chair approached all Faculties but no participation. REG Chair presented at Dec Research and Researcher Development Committee. Next step is to prepare a video to promote via Staff Roundup in line with launch of Researcher Guide (Sept 2023 TBC). No further action - Roadshows had low interest and may not be most efficient way to raise awareness. Continue to bring into all Faculty Research meetings, and documents. In all new docs - Induction, Researcher guide, 10 days committment, video on Canvas. | Awareness of Concordat is 34.6% (have some awareness) in 2023 CEDARS. | completed - no further action
|  | 1.3. Updates and resources made available and promoted via different channels including dedicated Concordat and ECR MS Teams channels, Canvas (UoS intranet), including Talking Heads video clip resources | No | Year 1 | REG | as above 1.1 |  | Spotlight on Concordat included in RIBE led research inductions as of October 2021 (held twice-yearly) and included in Faculty inductions from October 2022. Talking heads resource available on Research staff intranet (Canvas) and signposted in Research Bites blog October 2021. Included in new Induction Guide resource avalable from Sept 2022. Included in Researcher Development presentation in Corporate Induction March and May 2022. | All new staff have awareness via Induction Guide. Talking heads video remains as resource in staff resources. 66% were aware of the induction guide for research staff in CEDARS 2023. | completed - no further action
|  | 1.4. Inclusion in Research Strategy and Faculty Strategies (see PCDI1) | No | From Year 1 | DP Research & ADRs | as above 1.1 | ADR meeting forum for discussion and update on plans | Chair discussed at ADR 28 June 2022 meeting with DP Research to ensure in all Faculty Research strategies. Next discussed at ADR meeting June 2023 in light of development of new institutional strategy, new Research Strategy and Faculty strategies. | The Concordat will contribute to the Research & Innovation Strategy - and be considered when developing the underpinning in deliverable and operational plans. | carry forward - BAU
|  | 1.5. Inclusion in a Researcher Guide, Induction & Recruitment materials | No | From Year 2 | REG/HR&OD | as above 1.1 | REG subgroup for the Researcher Guide is Dr Hannah Hale (REG lead), Dr Allison Ford (Co-lead) | REG working group (led by ECR) with involvement of non-REG members, including as co-lead. The Researcher Guide is a new information resource for PIs and new staff to navigate policies, roles and expectations. Timeline of development activity was Oct 22- Feb 23 content drafting, Feb 2023 REG meeting draft shared for discussion, May 2023 shared with DP Research, RIBE and ADRs. Aug 2023 Graphics & Print, September/ October 2023 ready for Induction processes. | All new staff targetted with Induction Guide. 66% were aware of the induction guide for research staff in CEDARS 2023. All research staff will also recieve the new Researcher Guide. | completed - no further action
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | 2.1. Ensure institutional equality outcomes and supporting strategies e.g. Mental Health, Athena Swan, Anti-Racism are well communicated to researchers and managers | No | Ongoing | Dean EDI | Report on range of communications circulated to staff. Staff surveys indicate awareness of equality outcomes and strategies |  | University Court approved new strategies for Anti Racism and Race Equality, Mental Health, Gender Based Violence and Corporate Parenting in 2022. Staff and students were invited to engage in consultation, and the final versions were communicated through the staff and student communications channels. Each strategy is overseen by a steering group which includes a range of leads from Faculties and Professional Services. Part of the remit of the leads is to communicate the strategies, initiatives and progress through their teams. Further, the Equality, Diversity and Inclusion Forum (EDIF), which is chaired by the Dean of EDI, meets at least once a semester. This is an open forum and all staff are welcome to attend and share EDI issues and receive progress updates. The Dean of EDI is also a member of the Research Committee and the Research Environment Group, with EDI matters regularly appearing on the agenda for these meetings. | 73.4% of CEDARS 2023 respondents agree/strongly that UoS is committed to EDI (+3%). | completed - no further action
|  | 2.2 Promote researcher engagement in Athena Swan/Gender Equality Fora, and encourage participation in institutional Equality, Diversity and Inclusion Forum | No | From year 1 | Faculty Deans/Dean of EDI | Monitor membership of all EDI fora to see involvement of research active academic staff. First policy group meetings of academic year 2021/2 are set for Sept/Oct 2021 and and an update on membership will be provided to use as a baseline for future years. Monitoring of engagement on an annual basis. |  | All Faculties are invited to include representatives on all the EDI strategy groups, including the Gender Equality/Athena Swan group; the Gender Equality Group; the Health & Wellbeing Group; and the Anti Racism and Race Equality Group. RIBE and the IAS is also represented on the Gender Equality and Health and Wellbeing Groups. REG members asked to disseminate via local networks. Info included in the Sept 2022 IAS newsletter. No further uptake of research active staff as of July 2023. | A new EDI Manager in post August 2023 and there will be a restructuring of groups semester 1 2023. The proposal is to retain the Gender Equality Steering Group, which acts as the Institutional Self-Assessment Team for the purpose of Athena Swan and seek promote researcher engagement. | completed - no further action
|  | 2.3 Regular briefings of relevant policies/strategies communicated via Staff Roundup and Managers Network Newsletters | No | From Year 1 | HR&OD/CMR | Inclusion in Managers Network newsletter (published quarterly), inclusion in University-wide Staff Roundup 4 times p.a. |  | Regular updates on policies have been included in Staff round up and will continue on an ongoing basis (minimum 4.p.a). The Managers Network format is changing and under review Nov 2022. | Information has been communicated to line managers as per agreed regular schedule. | completed - no further action
|  | 2.4 Creation of Researchers Guide for induction purposes to raise awareness of policies relating to researcher life at Stirling. | No | From Year 2 | REG | Monitor awareness of promotion and redeployment processes as well as mechanisms to report incidents of discrimination/bullying/harassment and misconduct via CEDARS 2023 using CEDARS 2021 baseline data: familiarity with promotion pathways (43.8%), redundancy processes (16.3%), mechanisms to report discrimination (42.1%), bullying or harrassment ( 38.9%), misconduct (49.1%) | REG subgroup lead Dr Hannah Hale | REG working group (led by ECR) with involvement of non-REG members, including as co-lead. The Researcher Guide is a new information resource for PIs and new staff to navigate policies, roles and expectations. Timeline of development activity was Oct 22- Feb 23 content drafting, Feb 2023 REG meeting draft shared for discussion, May 2023 shared with DP Research, RIBE and ADRs. Aug 2023 Graphics & Print, September/ October 2023 ready for Induction processes. | Researcher Guide Complete. CEDARS 2023: familiarity with promotion pathways (49%), redundancy processes (16.8%), mechanisms to report discrimination (47.5%), bullying or harrassment (49.4%), misconduct (49.5%). Compared to baseline in 2021 this shows that there has been a significant increase in awareness of mechanisms to report bullying & harrassment (+10%), and a 5% increase in familiarity with promotion pathways and mechanisms to report discrimination. | carry forward
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | 6.1 Annual review of REG membership in terms of representation, engagement, contribution and sustainability. REG currently (October 2021) has representation from the Fixed Term Contract Researchers Forum. Membership recruitment will be managed via the ECR network. | No | Annually | REG | REG membership to include cross Faculty representation of a minimum of 1 fixed term contract researcher and a minimum of 2 Early Career Researchers. |  | Feb 2022 REG welcomed 2 new members: Research Fellow, FAH and Postdoctoral Research Fellow, FHSS. New Chair/Vice Chair structure implemented for succession planning: New Chair in post as REG Vice Chair from May 2022, taking on the role of REG Chair April 2023. Annual review of REG membership held in October 2021 and June 2023 - REG has a 19 strong membership with new members as per report document: ADR of Faculty of Arts & Humanities ii) Head of Employee Experience & Development (HR&OD) to ensure link in with organisation development plans and pulse survey work. Next annual review August 2023, ahead of that EOI open to fixed term research staff 28 June - 17 July. This action will become BAU as REG continues to monitor role representation as staff move into different posts/contracts, potential need to recruit new fixed-term contract researcher. | Full representation across roles and contract types. Involvement in REG activity also via wider subgroup activity. | completed - no further action
|  | 6.2 Promote participation in CEDARS 2023.Analysis of CEDARS 2021 data to feed into action plan focus and activity. | No | Year 2 | REG | CEDARS ran in June 2021 with a total of 164 responses gathered, of which 153 research staff (=26% response rate). Report on outcome in Research Bites blog in October 2021. Postively improve CEDARS 2023 response rates. | REG subgroup lead (REG Chair Prof Anna Whittaker). | Feedback from CEDARS 2021 helped shape the focus of the 2021-2023 action plan. A REG subgroup worked on the promotion and analysis of CEDARS 2023. CEDARS 2023 was open 31 March - 1 May 2023, total no. of responses 180, of which 173 research active staff (30% response rate). Quantitative and qualitative analysis under reviewed by subgroup May- July.Findings to be presented at REG 15 August 2023. | CEDARS 2023 completed by 27.5% staff up from 26% in 2021. Completed by 180 respondents of which 173 (86%) were staff as intended. | carry forward - BAU
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Participate in Corporate, Faculty and local Inductions, engage in building peer community via for example via the ECR MS Teams channel, consider membership of Fixed Term Contract Researchers Forum and/or other local postdoc forums to develop and contribute to peer to peer support networks. | No | Year 1 | Researchers/REG | Participation in induction and events will be monitored via attendance and feebdack data. |  | Centrally-led researcher inductions have been held biannually since October 2020, bringing together key areas of research support, including REG representation, and are offered to approx 50+ new research active staff and also open to all with an interest in attending, October and March each year. While attendance had increased from the first induction ( 25% attendance rate Oct 2020 to a 60% participation rate in March 2022), a decrease in attendance has been seen from Oct 2022 & March 2023: attendance at the Oct 2022 Researcher Induction (first hybrid induction event) was was lower than expected (30% attendance rate - 16 participants, 10 online and 6 in-person). A post event survey to participants gathered a 4.25 / 5 star rating (25% response rate) and a survey was also issued to those who did not attend to explore barriers to engagement. This survey however had a very low response rates ( < 15%) but findings would seem to indicate that attendance was affected by a lack of time and illness. The March 2023 induction was held fully online for greater accessibility and had a more targetted focus on institutional networks & activities (including REG), IAS & researcher development initiatives, grant funding support and ethics further to previous feedback received. 35% of new research staff attended (19 out of 55) and no survey feedback responses were however submitted. In addition to these RIBE-led inductions, there has also been RIBE participation in the University-wide HR led Induction events held in March & May 2022. | Attendance at induction events has decreased over 2022/23 in line with lower attendance generally noted across the board at events and researcher development activities/training. Feedback, while response rates are low, do show however consistently good satisfaction ratings (average 4/5). What we can see from induction is that there is greater subsequent interaction with the research eco-system (RIBE, IAS RDP, Stirling Crucible, Research Culture Conversations). | carry forward - BAU
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | 3.1 Implement the institutional Mental Health Strategy 2021-24. Roll out programme of mental health and wellbeing training for line managers. Enhance and promote network of staff involved in providing support for staff who are experiencing bullying or harassment. | No | From Year 1 | Dean EDI/HR&OD | Mental Health Training Programme rolled out. Completion rates monitored. Staff indicate awareness of policies and support in place to respond to bullying and harassment. Improve on CEDARS 2021 baseline of 38.9% strongly/agree they are familiar with institutional mechanisms to report bullying/harassment. |  | Mental health awareness development sessions for line managers and staff were launched which covered mental health and wellbeing; triggers and conditions; treatments and recovery; and creating a mentally healthy workplace. The Mental Health First Aid Course was also relaunched in 2021/22 with a further 21 members of staff being trained in this. The University implemented the Respect at Study and Work policy in 2021 which outlines mechanisms for reporting incidents on bullying and harassment. There is regular promotion of this in Staff roundup, specifically at the start of the new academic year. Mental Health training 2021/22 offered three courses, and there were in total 40 attendees. Mental Health training 2022/23 offererd three courses (different content) and in total there were 130 attendees. It has not been possible to determine how many attendees were researchers/managers of researchers. | From CEDARS 2023 71.9% of respondents felt confident in responding to any issues relating to bullying & harassment compared to 55.7% baseline in 2021 (+16.7%). Note no. of responses vary greatly 23 v 54. Furthermore, awareness of insitutional mechanisms for reporting bullying were 49.4% which is +10% compared to baseline 2021. | no further action - business as usual
|  | 3.2 Continue to offer a suite of resources for staff to help manage wellbeing and mental health including TogetherAll, the Employee Assistance Programme, and the Occupational Health Service | No | Ongoing | HR&OD | Monitor and review data provided on usage rates and evaluation of each of the resources provided |  | A range of resources are provided to support the mental health and wellbeing of employees. These include the Employee Assistance Programme which has a usage rate of 13% (this is well above average sector usage rate), Togetherall (subscription to online reosurces and community) , and a range of development opportunities including the reintroduction of the mental health first aid course and a series of wellbeing campaigns to promote health and wellbeing throughout the year (these included men’s health, mental health awareness week, wellbeing week, menopause awareness, back care, stress awareness. Mental Health training 2021/22 offered three courses, and there were in total 40 attendees. Mental Health training 2022/23 offererd three courses (different content) and in total there were 130 attendees. It has not been possible to determine how many attendees were researchers/managers of researchers. | From CEDARS 2023 45% knew about the health and wellbeing support options, over a third have some understanding of it. 17% had not heard of this. | no further action - business as usual
|  | 3.3 All staff encouraged via University news channels to complete 3 EDI online modules - EDI in the workplace, Unconscious Bias in the Workplace and Microbehaviours at Work as part of the staff induction process (see EI1). | No | Ongoing | HR&OD | Annual OD audit on number of completions . A baseline from 2022, monitor and review completion rates yearly. |  | Those who participate in interviews are required to complete an online training module. Interview panel members are reminded of this prior to participation. Completion rates for the recruitment and selection module: This has increased across the four years annually, and now completion is 2.5 x higher than in the initial 2019/20 year at 148 completions in 2022/23. Completion rates for Diversity in the Workplace module: This has increased across the four years annually, and now completion is 7 x higher than in the initial 2019/20 year at 118 completions in 2022/23. Completion rates for Unconscious Bias in the Workplace module: This has increased across the three years of availability, and now completion is 2 x higher than in the initial 2020/21 year at 101 completions in 2022/23. Completion rates for Microbehaviours module: This has increased across the three years of availability, and now completion is double that of the initial 2020/21 year at 101 completions in 2022/23. | The nature of the systems employed do not allow for an annual audit on number of completions by staff profile against total population. A breakdown of staff category (ie. research active staff) in completion data has previously provided a breakdown of Academic/Professional staff but this was through extensive manual checking. HR are investigating with the provider if academic/professional/research staff grouping can be automated to enhance reporting capabilities in relation to mandatory online learning. | completed - no further action
|  | 3.4 Implement the new Respect at Work and Study Policy (launched March 2021: Equality Impact Assessment carried out). Regular promotion at key transition points for staff, including at induction. | No | Year 1 | HR&OD | Measure awareness via an instituion specific question in CEDARS 2023 |  | The policy was implemented in 2021 and there is regular promotion of this in roundup, specifically at the start of the new academic year. CEDARS ran over April 2023. | Just under a third of respondents have an awareness of the Respect at Work policy in CEDARS 2023 (28.3% have some understanding); 33.3% know it exists but do not know the detail.Further work needed to raise profile. | no further action - business as usual
|  | 3.5 Review staff perception of workload via CEDARS 2023. | No | Year 2 | REG | Monitor via CEDARS. In CEDARS 2021 49.3% of respondents strongly/agree that their institution actively promotes the importance of good mental health & wellbeing of staff, with 31.3% in agreement that the working environment supports mental health & wellbeing. Furthermore 36.1% strongly/agree that they are treated fairly in relation to contracted workload. | REG subgroup lead (REG Chair Prof Anna Whittaker). | Feedback from CEDARS 2021 helped shape the focus of the 2021-2023 action plan. A REG subgroup worked on the promotion and analysis of CEDARS 2023. CEDARS 2023 was open 31 March - 1 May 2023, total no. of responses 180, of which 173 research active staff (30% response rate). Quantitative and qualitative analysis under reviewed by subgroup May- July.Findings to be presented at REG 15 August 2023. | In CEDARS 2023 57.8% of respondents strongly/agree that their institution actively promotes the importance of good mental health & wellbeing of staff (+8.5%), with a significant increase in those who agree that the working environment supports mental health & wellbeing at 49.5 (+18.2%). Furthermore 40.7% strongly/agree that they are treated fairly in relation to contracted workload ( +4.6)% compared to CEDARS 2021 baseline. 55% believe we are understaffed. | no further action - business as usual
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | 4.1 Roll out Mental Health and wellbeing managers development programme and associated EDI training programme, First Responder, and preventing gender based violence training. Expectation that all Line Managers will undertake EDI training (e.g EDI in the workplace, microbehaviours, unconscious bias), including mental health awareness. | No | Year 1 | HR&OD | Annual OD audit on number of completions . A baseline from 2022, monitor and review completion rates yearly. |  | As part of the approach to prioritise and raise awareness of positive health and wellbeing, the University re-launched an SQA accredited “First Aid for Mental Health” training programme. The programme was suspended during the pandemic as providers were unable to deliver this online. A further 21 staff participated in the programme, bringing the total of those who have attended the programme to 72. Feedback for this course continues to be positive. Mental health awareness development sessions for line managers and staff (3 of each session)were launched which covered mental health and wellbeing; triggers and conditions; treatments and recovery; and creating a mentally healthy workplace. A programme of First Reponder training and GBV training was also rolled out with an induction module on GBV also being introduced (we are unable to monitor uptake of the online module). In addition, a number of staff wellbeing programmes were offered covering topics including mindfulness, personal resilience and positive mindset. A mental health and wellbeing session, led by the Dean for Equality, Diversity and Inclusion (Chair of Mental Health and Wellbeing group) was incorporated into the corporate induction programme. A number of campaigns have been delivered over the course of the year to promote and raise awareness of mental health and wellbeing. These have included Menopause Awareness month, Wellbeing week and Mental Health Awareness week. There are 3 online modules for EDI and there is an expectation the staff complete these, however it is not possible to obtain completion rates for these modules. | Unable to quantify impact at institutional level. Anecdotal feedback indicates these opportunities have a positive impact on individual wellbeing. From CEDARS 2023 45% knew about the health and wellbeing support options, over a third have some understanding of it. 17% had not heard of this. | no further action - business as usual
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | Undertake the mental health and wellbeing training for line managers and training in Achieving Success for PIs ( see ECI3 & EI5). Regularly monitor sickness/absence/annual leave to ensure wellbeing of research staff, raising issues where appropriate. Raise awareness of Respect at Work and Study Policy and various reporting mechanisms, addressing behvaiour where appropriate. | No | From Year 1 | Managers of Researchers/HR&OD | Annual OD audit on number of completions . A baseline from 2022, monitor and review completion rates yearly. |  | As part of the approach to prioritise and raise awareness of positive health and wellbeing, the University re-launched an SQA accredited “First Aid for Mental Health” training programme. The programme was suspended during the pandemic as providers were unable to deliver this online. A further 21 staff participated in the programme, bringing the total of those who have attended the programme to 72. Feedback for this course continues to be positive. Mental health awareness development sessions for line managers and staff (3 of each session)were launched which covered mental health and wellbeing; triggers and conditions; treatments and recovery; and creating a mentally healthy workplace. A programme of First Reponder training and GBV training was also rolled out with an induction module on GBV also being introduced (we are unable to monitor uptake of the online module). In addition, a number of staff wellbeing programmes were offered covering topics including mindfulness, personal resilience and positive mindset. A mental health and wellbeing session, led by the Dean for Equality, Diversity and Inclusion (Chair of Mental Health and Wellbeing group) was incorporated into the corporate induction programme. A number of campaigns have been delivered over the course of the year to promote and raise awareness of mental health and wellbeing. These have included Menopause Awareness month, Wellbeing week and Mental Health Awareness week. There are 3 online modules for EDI and there is an expectation the staff complete these, however it is not possible to obtain completion rates for these modules. | Unable to quantify impact at institutional level. Anecdotal feedback indicates these opportunities have a positive impact on individual wellbeing. From CEDARS 2023 45% knew about the health and wellbeing support options, over a third have some understanding of it. 17% had not heard of this. | no further action - business as usual
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | Maintain awareness of and updates in Family friendly policies and guidance, including the Flexible Working policy, Parental Leave, Time off for Dependants, and Agile working. | No | Ongoing | Managers of Researchers/HR&OD | Monitoring of flexible working requests |  | Flexible requests are official requests to change days/hours of work and are not monitored by HR. Line managers receive the flexible working request and HR Partners will discuss with the line manager to determine whether the request can be accommodated to ensure the policy is followed. The implementation of the new AGILE working framework in August 2021 has in some way superseded the need for official flexible working requests as staff have greater flexibility in their working pratice (hours and place) with a greater emphasis on outcomes and managed locally in line with business need. Considering both these elements, awareness of policies should be monitored via CEDARS 2023. | CEDARS 2023 showed awareness of agile working policy was 45.6%. 25% of research staff invited to participate in the Agile Working pulse survey submitted a response. 73% of research staff reported a positive experience of the Agile Working Framework -this is 7% lower than the institutional norm. Research staff responded less favourably for questions in relation to: o The principles and personas help me understand how agile working can apply to me. o I am aware of the Agile Working Framework o My line manager focusses on outcomes as part of my team’s agile working arrangements o Agile working allows me to develop relationships and connections with my team Responses were considerably less favourable for research staff who have been at the University for more than 5 years Responses from research staff identifying as male were considerably more favourable than those identifying as female. The verbatim comments (20) recieved were largely positive; particularly in relation to being trusted to work autonomously and improved work/life balance. There are, however, some mentions of the impact of reduced face to face collaboration as well as a general lack of awareness of the Framework. | completed - no further action
ECR3 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | Discuss wellbeing in Achieving Success conversations, engage in peer networks, make use of available resources/tools | No | Ongoing | Researchers/HR&OD | Monitor and review data provided on usage rates and evaluation of each of the resources provided. (see ECI3) |  | Occupational health support usage: Employee Assistance Programme – period 01/03/2022 – 28/02/2023 usage rate is 15%. The EAP has been in place for almost 3 years and the usage rate has remained consistently between 13% - 15%. This is a good usage rate as the norm (not HEI specific) would be around 4-5%. At the moment we do not have evaluation data and this is something we are working with the provider on. What we do know is that of those referred for counselling, 85.7% self-declare improvements from pre & post intervention survey. Attendance at mental health programme. The majority of attendances are professional services roles. Mental Health training 2021/22 offered three courses, and there were in total 40 attendees. Mental Health training 2022/23 offererd three courses (different content) and in total there were 130 attendees. It has not been possible to determine how many attendees were researchers/managers of researchers. | Information has been provided in cell 41J. Not possible to quantify impact against this information due to confidential nature of EAP. | no further action - business as usual
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | Implement the institutional Mental Health Strategy 2021-24. Roll out programme of mental health and wellbeing training for line managers. Enhance and promote network of staff involved in providing support for staff who are experiencing bullying or harassment. | No | From Year 1 | Dean EDI/HR&OD | Mental Health Training Programme rolled out. Completion rates monitored. Staff indicate awareness of policies and support in place to respond to bullying and harassment. Improve on CEDARS 2021 baseline of 38.9% strongly/agree they are familiar with institutional mechanisms to report bullying/harassment. |  | Mental health awareness development sessions for line managers and staff were launched which covered mental health and wellbeing; triggers and conditions; treatments and recovery; and creating a mentally healthy workplace. The Mental Health First Aid Course was also relaunched in 2021/22 with a further 21 members of staff being trained in this. The University implemented the Respect at Study and Work policy in 2021 which outlines mechanisms for reporting incidents on bullying and harassment. There is regular promotion of this in roundup, specifically at the start of the new academic year. |  | completed - no further action
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | Undertake the mental health and wellbeing training for line managers and training in Achieving Success for PIs ( see ECI3 & EI5). Regularly monitor sickness/absence/annual leave to ensure wellbeing of research staff, raising issues where appropriate. Raise awareness of Respect at Work and Study Policy and various reporting mechanisms, addressing behvaiour where appropriate. | No | From Year 1 | Managers of Researchers/HR&OD | See ECM1 |  | See ECM1. This action does not have a specific action as in the original template the ECM3 obligation previously comprised wellbeing, mental health, discrimination, bullying, harrassment and research integrity. The 2021-2023 action plan was transposed onto the new template and hence is blank.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | Familiarise and maintain awareness of the Respect at work and Study Policy and Guidelines for Handling allegations of misconduct in research | No | Ongoing | Researchers | Monitor awareness of reporting mechanisms via CEDARS 2023 | REG will monitor awareness | Feedback from CEDARS 2021 helped shape the focus of the 2021-2023 action plan. A REG subgroup worked on the promotion and analysis of CEDARS 2023. CEDARS 2023 was open 31 March - 1 May 2023, total no. of responses 180, of which 173 research active staff (30% response rate). Quantitative and qualitative analysis under reviewed by subgroup May- July.Findings to be presented at REG 15 August 2023. | CEDARS 2023 showed 28.3% awareness of Respect at work policy and 18.3% awareness of Guidelines for handling allegations of misconduct. Further work is required to raise awareness of these. A +10% increase in familiarity wth institutional mechanisms to report bullying & harrassment (agree/agree strongly 49.4% v 38.9%) is noted. | Carry forward
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | Roll out Mental Health and wellbeing managers development programme and associated EDI training programme, First Responder training, and preventing gender based violence. Expectation that all Line Managers will undertake EDI training (e.g EDI in the workplace, microbehaviours, unconscious bias), including mental health awareness. | No | Year 1 | HR&OD | Annual OD audit on number of completions . A baseline from 2022, monitor and review completion rates yearly. |  | As part of the approach to prioritise and raise awareness of positive health and wellbeing, the University re-launched an SQA accredited “First Aid for Mental Health” training programme. The programme was suspended during the pandemic as providers were unable to deliver this online. A further 21 staff participated in the programme, bringing the total of those who have attended the programme to 72. Feedback for this course continues to be positive. Mental health awareness development sessions for line managers and staff (3 of each session)were launched which covered mental health and wellbeing; triggers and conditions; treatments and recovery; and creating a mentally healthy workplace. A programme of First Reponder training and GBV training was also rolled out with an induction module on GBV also being introduced (we are unable to monitor uptake of the online module). In addition, a number of staff wellbeing programmes were offered covering topics including mindfulness, personal resilience and positive mindset. A mental health and wellbeing session, led by the Dean for Equality, Diversity and Inclusion (Chair of Mental Health and Wellbeing group) was incorporated into the corporate induction programme. A number of campaigns have been delivered over the course of the year to promote and raise awareness of mental health and wellbeing. These have included Menopause Awareness month, Wellbeing week and Mental Health Awareness week. There are 3 online modules for EDI and there is an expectation the staff complete these, however it is not possible to obtain completion rates for these modules. | We are currently unable to provide data on how many line managers we have at the University, therefore unable to expand on this answer further. | no further action - business as usual
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | Undertake 3 EDI online training modules (EDI in the workplace, Unconscious Bias and Microbehaviours - see ECI3) | No | Ongoing | Researchers/HR&OD | Annual OD audit on number of completions . A baseline from 2022, monitor and review completion rates yearly. |  | Those who participate in interviews are required to complete an online module. Interview panel members are reminded of this prior to participation. Completion rates for the recruitment and selection module: This has increased across the four years annually, and now completion is 2.5 x higher than in the initial 2019/20 year at 148 completions in 2022/23. Completion rates for Diversity in the Workplace module: This has increased across the four years annually, and now completion is 7 x higher than in the initial 2019/20 year at 118 completions in 2022/23. Completion rates for Unconscious Bias in the Workplace module: This has increased across the three years of availability, and now completion is 2 x higher than in the initial 2020/21 year at 101 completions in 2022/23. Completion rates for Microbehaviours module: This has increased across the three years of availability, and now completion is double that of the initial 2020/21 year at 101 completions in 2022/23. | The nature of the systems employed do not allow for an annual audit on number of completions by staff profile against total population. A breakdown of staff category (ie. research active staff) in completion data has previously provided a breakdown of Academic/Professional staff but this was through extensive manual checking. HR are investigating with the provider if academic/professional/research staff grouping can be automated to enhance reporting capabilities in relation to mandatory online learning. | carry forward as investigate possibilties to enhance reporting capabilities
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | 1. A dedicated Safeguarding Policy for Research Activities was approved in Dec 2020. Raise awareness of this policy in the Research Induction, in the Researcher Guide, inclusion in policy spotlights series in newsletters, self-learning resources available. 2. Development of a research integrity action plan by March 2022. 3. Dean for Research Engagement and Performance appointed in 2019. Continue to build on and further develop the research culture series of initiatives. Embed research culture, including expectations and activities around research integrity, into the institutional research strategy. 4. New Ethics Review Manager (ERM) launched October 2020 with institution wide training sessions run in academic year 2021-22. A guide, helpdesk service and video resources available and clearly signposted to research staff. The introduction of ERM ensures consistency of review across the University and highlights the importance of research integrity by ensuring that all researchers are aware of their requirements. Support for ethics and research integrity as a core activity is clearly communicated through the Researchers Guide and Staff Induction process. 5. Researchers to maintain awareness of University policies and procedures and developments in sector best practuce. Signposting of appropriate resources in the Researcher Guide. Engage in and promote engagement in the research culture series of inititiaves around ethics, integrity and safeguarding (see ECI5). | No | Actions 1 & 2 & 4 Year 1; Actions 3 & 5 Year 2 (Researcher Guide & research culture initiatives) | RIBE / Dean REP / Managers of Researchers / IAS | 1. Resources made available on website. Monitor awareness of policy via CEDARS 2023 2. Resources made available on website 3 & 5. Event engagement rates monitored 4. Resources available on website. Monitor improvement in perception/rating of research integrity from CEDARS 2021 baseline of 61.6% very/good and awareness of the Concordat to Support Research Integrity (some understanding 25.9%). |  | 1. Policy incuded in A-Z policy and guidelines page and all new staff signposted via Induction guide, issued Nov 2022. 2. Work on the Research Integrity action plan has not progressed due to conflicting team priorities. The new Research & Innovation Strategy 2023-30 is being developed and RI will play a core part of this. The new startegy will go for approval to Court in Dec 2023 afterwhich delivery plans will be developped across all areas of the RIBE directorate which will outline plans including activity relating to RI. RIBE delivery plans will be developed over semester 2 AY 2023/24 and RI plans will be incorporated in the 2023-26 plan from year 2. 3. Research Culture is embedded into the draft Research Strategy with 7 dedicated Research Culture Conversations (RCC) launched AY 22/23 to explore and define a common understanding of what a healthy research culture looks like /a succesful reesearcher/ good leadership/supportive environment/inclusive culture/how to enable impact and next steps for Stirling. 4. Resources available on IAS Canvas module (intranet) and website. Ethics a core part of biannual Researcher Induction. | 1. Less than a quarter have an awareness of the safeguarding research policy as reported in the CEDARS 2023 (23%), with just under 40% know that this exists but do not now the detail. 3. 80% of total attendances at the RCC events were research active staff (136/ 168) which saw 80 individual research staff engaging. The average rating was 4.3/5 stars. 4. 68% agreed that Research Integrity (including the ethical approval process) was good/very good in CEDARS 2023 - Stirling specific questions (+6.3%), and three quarters agree that their institution promotes the highest standards of research integrity (+4% on CEDARS 2021 baseline). All researchers will be signposted to policies via new Researcher Guide from Sept 2023. | carry forward
ECM3 | Ensure managers report and address incidents of poor research integrity. | Raise awareness of Respect at Work and Study Policy and various reporting mechanisms, addressing behaviour where appropriate. | No | From Year 1 | Managers of Researchers/HR & OD | Measure awareness via CEDARS |  | As part of our commitment to the Concordat for Research Integrity we need to make an annual report on our research integrity activities. The report includes the number of formal allegations the University investigates – currently the number is 0. The report will be approved at the Nov 2022 meeting of UREC. Previous reports are available here: https://www.stir.ac.uk/research/research-ethics-and-integrity/governance/annual-statement-on-research-integrity/ | From CEDARS 2023 over one third were not aware of the Respect and work and study policy, one third knew it existed, just under a third had some understanding of it. 68% agreed research integrity including the ethical approval process was good to very good. There had been a slight improvement from 2021 on the views about research integrity and ethical approval processes with more viewing these as very good than in 2021. The majority (about half) of respondents still rated this as good. | no further action - business as usual
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | Maintain highest standards of research integrity through engagement with Ethics Review Manager, maintaining awareness of institutional policies and practice relating to good data managment, ethics and research integrity, participating in research culture series of events ( see ECI5 ) | No | Ongoing | Researchers/Research Integrity & Governance Manager/HR |  |  | This action in the old template included acting in accordance with EDI also and we put Annual OD audit on number of completions as a success measure to establish a baseline from 2022 to then monitor and review completion rates yearly. |  | no further action - business as usual
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | Familiarise and maintain awareness of the Respect at work and Study Policy and Guidelines for Handling allegations of misconduct in research | No | Ongoing | Researchers | Monitor awareness of reporting mechanisms via CEDARS 2023 |  | A REG subgroup worked on the promotion and analysis of CEDARS 2023. CEDARS 2023 was open 31 March - 1 May 2023, total no. of responses 180, of which 173 research active staff (27.5% response rate). Quantitative and qualitative analysis under reviewed by subgroup May- July.Findings to be presented at REG 15 August 2023. | CEDARS 2023 showed 28.3% awareness of Respect at work policy and 18.3% awareness of Guidelines for handling allegations of misconduct. Around 50% agree/agree strongly they are familiar with reporting mechanisms to report incidents of misconduct, this is unvaried from 2021 CEDARS baseline. There has however been a +10% increase in familiarity wth institutional mechanisms to report bullying & harrassment (agree/agree strongly 49.4% v 38.9%). Further work is required to raise awareness of reporting mechanisms. | no further action - business as usual
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | Encourage and report on membership/representation of contract researchers on all Faculty Research Committees, REG and other Policy Groups *e.g. Athena Swan, EDI, Mental Health & Wellbeing | No | From Year 1 | REG/Deans/ADRS | Annual monitoring of how many researchers are currently involved REG and Faculty Research committees . First policy group meetings of academic year 2021/2 are set for Sept/Oct 2021 and and an update on membership will be provided to use as a baseline for future years. Monitoring of engagement on an annual basis. |  | All Faculties are invited to include representatives on all the EDI strategy groups, including the Gender Equality/Athena Swan group; the Gender Equality Group; the Health & Wellbeing Group; and the Anti Racism and Race Equality Group. RIBE and the IAS is also represented on the Gender Equality and Health and Wellbeing Groups. REG members asked to disseminate via local networks. Info included in the Sept 2022 IAS newsletter. No further uptake of research active staff as of July 2023. A new EDI Manager will be taking up post July 2023 and there will be some restructuring of groups late 2023. Further engagement work needed also to link in with Athena Swan initiatives and surveys. | The final structure of the EDI groups is still to be finalised. The intention is to have the new structure in place for the forthcoming Academic Year. The proposal is to retain the Gender Equality Steering Group, which acts as the Institutional Self-Assessment Team for the purpose of Athena Swan and seek promote researcher engagement. All researchers encouraged to become committee members in new Researcher Guide. | carry forward
ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | Actively participate in and promote researcher engagement in EDI fora, Faculty Research Committees, and research culture development work. (see ECI2 & ECI5). | No | From Year 1 | Managers of Researchers/REG | Monitoring of membership of researcher engagement in policy fora (see ECI2). |  | All Faculties are invited to include representatives on all the EDI strategy groups, including the Gender Equality/Athena Swan group; the Gender Equality Group; the Health & Wellbeing Group; and the Anti Racism and Race Equality Group. RIBE and the IAS is also represented on the Gender Equality and Health and Wellbeing Groups. REG members asked to disseminate via local networks. Info included in the Sept 2022 IAS newsletter. No further uptake of research active staff as of July 2023. A new EDI Manager will be taking up post July 2023 and there will be some restructuring of groups late 2023. Further engagement work needed also to link in with Athena Swan initiatives and surveys. For engagement in Research Culture activity see ECI5 line 53. | EDI Fora: The final structure of the EDI groups is still to be finalised. The intention is to have the new structure in place for the forthcoming Academic Year. The proposal is to retain the Gender Equality Steering Group, which acts as the Institutional Self-Assessment Team for the purpose of Athena Swan and seek promote researcher engagement. RCC: 80% of total attendances at the RCC events were research active staff (136/ 168) which saw 80 individual research staff engaging. The average rating was 4.3/5 stars. | carry forward
EM5 | Engage with opportunities to contribute to relevant policy development within their institution. | Actively engage in and encourage researcher staff engagement in opportunities to contribute to policy via membership of institutional Policy Groups (including for example Athena Swan, Race Equality, Gender based violence Group, Gender Equality) as well as engaging in research specific development work related to Research Culture. | No | From Year 1 | Managers of Researchers/REG | First EDI policy group meetings of academic year 2021/2 are set for Sept/Oct 2021 and an update on membership will be provided to use as a baseline for future years. Provide updates on research related policy development via spotlights and Research bites series. |  | All Faculties are invited to include representatives on all the EDI strategy groups, including the Gender Equality/Athena Swan group; the Gender Equality Group; the Health & Wellbeing Group; and the Anti Racism and Race Equality Group. RIBE and the IAS is also represented on the Gender Equality and Health and Wellbeing Groups. REG members asked to disseminate via local networks. Info included in the Sept 2022 IAS newsletter. No further uptake of research active staff as of July 2023. A new EDI Manager will be taking up post July 2023 and there will be some restructuring of groups late 2023. Further engagement work needed also to link in with Athena Swan initiatives and surveys. For engagement in Research Culture activity see ECI5 line 53. | EDI fora: The final structure of the EDI groups is still to be finalised. The intention is to have the new structure in place for the forthcoming Academic Year. The proposal is to retain the Gender Equality Steering Group, which acts as the Institutional Self-Assessment Team for the purpose of Athena Swan and seek promote researcher engagement. RCC: 80% of total attendances at the RCC events were research active staff (136/ 168) which saw 80 individual research staff engaging. The average rating was 4.3/5 stars. | carry forward
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | Participate in institutional Research Culture initiatives including Festival of Research event series, REG membership, Faculty Committee membership and other researcher fora. | No | From Year 1 | Researchers/REG | Monitor engagement in events via attendance and evaluation data and membership in policy fora. |  | Festival of Research 2023 saw 392 attendances (272 in-person, 120 online) and a total of 115 individuals engaging with the 2-week programme, 69 of which were research active staff (=12% engagement rate), 25 PGRs and 19 professional services staff supporting research. This engagement/attendance is broadly in line with Festivals 2022, 2021 & 2020. Overall rating of Festival year on year sits consistently at around 4.4/5 stars with a 95% recommend rate. Festival is an annual series of events committed to stimulatung discussiona round topics of interest to the researcher comunty and a platform to showcase research and future plans and facilitate networking opportunites. REG Subgroups were created to coordinate the delivery of REG activities and were highly successful in delivering key actions. This model of engagement was also adopted for year 2 activities and was expanded to also comprise research active staff from outwith REG membership to ensure greater inclusivity and representation of researcher voices. Applications were open via an EOI. In the longer term, participation in REG subgroups may also facilitate succession planning as subgroup participants can apply for REG membership. There were 6 subgroup activities in total working on CEDARS, Research Culture initiatives, Researcher Guide development, recruitment, promotion and career advancement guidance, DORA and professorial colloquia, all comprised research active staff within REG, including 5 colleagues out with REG (1 research fellow, 1 senior research fellow, 1 research assistant and 1 Senior Lecturer). As of Feb 2022 REG had 2 new members: Research Fellow, FAH and Postdoctoral Research Fellow, FHSS, both members also sit on Faculty Research Committees to ensure alignment and dissemination of activity. the Head of Employee Experience & Development (HR&OD) joined REG in May 2023 to ensure alignment with new HR People & Culture strategy (ETA Dec 2023 to Court). New Chair/Vice Chair structure implemented for succession planning. New Chair in post as REG Vice Chair from May 2022, taking on the role of REG Chair April 2023. Next annual review of REG membership in August 2023 meeting. An EOI is currently open for new contract research staff members (June-July 2023). | 1. Engagement in Research Culture: There are now 12 Research Culture Champions engaged in regular meetings every 3 months with the Dean for Research Engagement. This network was established late 2022 to share good practice that is highlighted in the annual Research Culture Awards, which take place during the annual Festival of Research since 2019. Dean REP and the network hosted 7 monthly Research Culture Conversations open to all Nov 2022-June 2023 (see ECI5 line 53). 2. Festival of research 2023 reached 69 research active staff (12%) and overall rating of 4.4 out of 5 for satisfaction which in line with previous years. There was a 15% increase in engagement with the Research Culture Awards (286 nominations in 2023). 3. REG memberships: ADR for FAH and a lecturer (FoSS) joined REG in June 2023 and we are recruiting via EoI new contract researchers across the faculties including RFs from FoSS, FNS and SMS. | carry forward
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | Participate in internal research focussed fora such as the Fixed Term Contract Researchers Forum, Faculty Research Committees and REG related initiatives. Engage in CEDARS, ECR teams and other local networks and Festival of Research activities. Explore and participate in external opportunities, sector surveys, national groups and sector-led intiatives. | No | From Year 1 | Researchers | Internal engagement can be monitored via baseline membership data, and/or event attendance. |  | REG has established itself as an inclusive and engaged forum which actively works to improve the research environment of the University. To ensure broad representation and maximise dissemination of activities via local networks REG has developed a strong cross-Faculty academic representation of 11 research-active staff members. It has welcomed two new early career researchers AY 2021/22 (a Research Fellow and Postdoctoral Research Fellow). Furthermore, in the last year a chair-vice chair structure has been established for succession planning purposes. Subgroups were created to coordinate the delivery of REG activities. Each working group was led by at least two REG members, with further participation drawn from within REG or across the University. This model of engagement has proven highly successful in delivering key actions and in enabling wider participation of staff from across the University in developing the university research environment and research culture. | CEDARS 2023 engagement was 30%. Research Festival reached 69 research active staff (12%). The Fixed Term Researcher Forum (FoSS) has approx. 25 members. | carry forward
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | 1a Institutional Athena SWAN renewal (Bronze) will be submitted end January 2022. 1b Divisional Athena SWAN groups - Bronze awards held in BES, IoA, Psychology and Faculty awards in FHSS, FSS and recently (July 2021) in SMS. | Yes | 1.1 Submit January 2022 (Results by spring 2022) | Dean EDI | Awards submitted and achieved |  | The University retains a Bronze institutional award and is working towards submitting a Bronze renewal November 2023. FHSS & BES will shortly commence working in their renewal application (end date April 2024). |  | no further action - business as usual
|  | 2. Staff undertaking interviews must complete online training module for Managers prior to undertaking interview panels (Unconscious Bias training see ECI4 ) | No | Ongoing | HR &OD | Annual OD audit on number of completions . A baseline from 2022, monitor and review completion rates yearly. |  | see J50 | SEE K50 | no further action - business as usual
|  | 3. Explore including statements of the University's commitment to EDI into all job adverts and recruitment and selection processes. | No | From Year 1 | HR&OD/Faculty Deans | Number of Faculties/Divisions who have begun to adopt the inclusion of specific EDI criteria into recruitment processes. |  | All adverts now contain a statement relating to EDI – “The University of Stirling recognises that a diverse workforce benefits and enriches the work, learning and research experiences of the entire campus and greater community. We are committed to removing barriers and welcome applications from those who would contribute to further diversification of our staff and ensure that equality, diversity and inclusion is woven into the substance of the role. We strongly encourage applications from people from diverse backgrounds including gender, identity, race, age, class, and ethnicity.” | Statements included on all job adverts. Hiring managers mandatory to undertake recruitment and selection training before sitting on a panel. Responsibility for ensuring EDI in recruitment and selection sits with hiring managers and panels. | no further action - business as usual
|  | 4. Raise awareness of Recruitment Guidance via Managers Network policy spotlights | No | Year 1 | HR &OD | Inclusion in Managers Network newsletter ( 4 times p.a.) |  | The Manager's Network newsletter format is being reviewed. Awareness is being raised in HR Partner discussions. The recruitment guidance is also currently under review. | HRPs ensure adherence to recruitment guidance as part of local level discussions. | carry forward
|  | 5. Include guidance on research contract appropriate grades within Researcher Guide | No | From Year 2 | HR&OD/RIBE/REG | Guidance provided in Researcher Guide | REG subgroup for the Researcher Guide is Dr Hannah Hale (REG lead), Dr Allison Ford (Co-lead) | REG lead for this subgroup is and ECR from FoSS, also chair of the Fixed Term Contract Researchers Forum in FoSS, co-lead by non REG member Research Fellow, FHSS.Call for engagement Aug 2022 open to all with an interest. The Researcher Guide is a new information resource for PIs and new staff to naviagte policies, roles and expectations. Timeline of development activity was Oct 22- Feb 23 content drafting, FEB 7 REG meeting draft 1 shared for discussion, May shared with DP Research, REG, RIBE.and ADRs. June -July Graphics & Print, September October 2023 ready for Induction processes. | Researcher Guide launched Sept/Oct 2023 | completed - no further action
|  | 6. Increase awareness of the Declaration on Open Research (DORA) undersigned by UoS in March 2020 and its principles of responsible metrics via a) the creation of a guide to responsible research assessment made available through the Research Integrity webpages along with the set of principles used by the University in its approach to research assessment. b) Develop training session on "What is responsible and fair research assessment and what does it mean for me" | No | From Year 2 | Dean REP & HR & OD/REG | Materials developed.Provide a baseline of awareness via institutional questions in CEDARS 2023. Monitor and report attendance and feedback of training session annually. | REG subgroup is led by Prof Rachel Norman (Dean REP) | REG subgroup formed.Update as of Feb 2023 DORA meetings postponed due strikes but there is now a better understanding of where the responsibility for this lies (REG) and a process in place to get a policy drafted and we have been looking at good practice elsewhere. This work was postponed due to ongoing work by HR. | Work will continue re DORA awareness and implementation via a REG subgroup, led by our Dean for REP. | carry forward
|  | 7. Clear guidance should be developed for staff involved in recruitment and promotion. Guidance should include unambiguous instruction against the inappropriate use of publication metrics and advice on the use of a wide range of research outputs. Criteria used for recruitment, promotion or career advancement should be transparent and refer to the principles. | No | From Year 2 | Dean REP & HR & OD/REG | Materials developed. In CEDARS 2021 85.7% of respondents felt fully/confident in their ability to use inclusive, equitable and transparent recruitment processes. Increase in awareness and confidence will be monitored via CEDARS 2023 | REG subgroup is co-led by Prof Rachel Norman and Jennifer Paton (Head of HR Partnering) | REG subgroup formed. Update Feb 2023: This action will now progressed by HR with REG input. Guidance on recruitment and promotion is available and is clearly set out. No further action required. | In CEDARS 2023 96.8% of respondents felt fully/confident in their ability to use inclusive, equitable and transparent recruitment processes. This is an increase of 11% compared to baseline CEDARS 2021. | no further action - business as usual
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | Research Staff Induction events to run once per semester as part of the wider Corporate Induction (pilot scheme launched 2020-21). Promote these events as an opportunity to support new staff to understand our structure and organisation. | No | Ongoing | HR & OD, Dean REP, Dean IAS, RIBE | 20% of all eligible staff to attend a session. Gather data on attendance and feedback. Monitor value of institutional induction via CEDARS, improving on 2021 baseline of 28.6% of respondents finding the institutional induction very/useful. | RIBE | Centrally-led researcher inductions have been held biannually since October 2020, bringing together key areas of research support, including REG representation, and are offered to approx 50+ new research active staff and also open to all with an interest in attending, October and March each year. While attendance had increased from the first induction ( 25% attendance rate Oct 2020 to a 60% participation rate in March 2022), a decrease in attendance has been seen from Oct 2022 & March 2023: attendance at the Oct 2022 Researcher Induction (first hybrid induction event) was was lower than expected (30% attendance rate - 16 participants, 10 online and 6 in-person). A post event survey to participants gathered a 4.25 / 5 star rating (25% response rate) and a survey was also issued to those who did not attend to explore barriers to engagement. This survey however had a very low response rates ( < 15%) but findings would seem to indicate that attendance was affected by a lack of time and illness. The March 2023 induction was held fully online for greater accessibility and had a more targetted focus on institutional networks & activities (including REG), IAS & researcher development initiatives, grant funding support and ethics further to previous feedback. 35% of new research staff attended (19 out of 55) and no survey feedback responses were however submitted. In addition to these RIBE-led inductions, there has also been RIBE participation in the University-wide HR led Induction events held in March & May 2022. | CEDARS 2023 showed 61.8% found departmental/local induction useful/very useful (+19% compared to baseline 2021). Institutional induction has also improved with 41.8% (+13.2%) rating the induction useful/very useful in CEDARS 2023 compared to 2021 baseline. | carry forward - BAU
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | Ensure that success and effort at grant capture are recognised and celebrated by the University. | Yes | Ongoing | ADRs/CMR | Via Faculty Newsletters and Staff RoundUp |  | Faculty newsletters include regular spotlights where appropriate. FNS has a monthly newsletter, FSS a weekly newsletter, while SMS & FAH have less established /frequent newsletters. FHSS now has Teams newspage with regular updates. | Spotlights included by faculties in their internal communications. | no further action - business as usual
|  | University policy supports Researchers to apply for promotion during the course of externally funded grants . Raise awareness of the Academic / Research Advancement Guidance by 1) including in the Researcher Guide, 2) encouraging discussion in AS with ECRs 3) via policy highlights in Staff Roundup and Managers Network newsletters. 4) with dedicated ECR & woman only Preparing for Promotions training sessions | No |  | REG/HR&OD/CMR | Analysis and reporting of applications post promotion rounds (HR&OD) | REG subgroup for Researcher Guide | Development sessions are offered to managers and individuals for achieving success. Academic Promotions criteria is widely publicised and there is a dedicate sharepoint site which is available to staff and contains guidance, criteria, promotion routes and process. The preparing for promotions sessions were very well attended for the last round of APC and these will be running again for this promotion round. There is a preparing for promotions session for all staff and a dedicated one for underrepresented groups and this will continue this year. No dedicated ECR session. Researcher Guide development underway in year 2, draft shared May 2023, G&P ETA Aug, September /October ready for new AY. | Researcher Guide reaches all research staff. CEDARS 2023 shows About 50% have some understanding of academic advancement and promotions committee guidance, only 16% had never heard of it. | no further action - business as usual
|  | 3.4 Raise awareness of the annual Recognition Award Scheme (RAS) which recognises staff commitment and achievements with a tangible reward for a sustained or specific exceptional contribution. Staff with 12mths service can be nominated for a one-off cash sum payment or an accelerated additional increment, with nominations for the award scheme via Dean of Faculty on recommendation of Line Manager. Include in policy spotlights, embed in in-house Leadership training programme and include in Researcher Guide. | No | Year 1 (Awareness) Year 2 (Researcher Guide) | HR & OD/CMR | A baseline of previous years' awards will be used to monitor research staff nominations. Review in July 2022. | REG subgroup for Researcher Guide | The Recognition Award Scheme (RAS) was published in Staff Roundup and there was wide promotion to Managers. HR Partners promoted and discussed this with the Managers in their areas. There was a dedicated sharepoint created in 2022 which contained guidance, timeline, and staff stories. RAS was included in the Researcher Guide under development year 2 (circulation AY 2023/24) | Researcher Guide reaches all research staff. Data on RAS shows 1 research staff member received a recognition award in 2021/22 (50% success rate) and 1 in 2022/23 (100% success rate). | carry forward - BAU
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers. | Undertake EDI training programme - EDI in the workplace, Unconscious Bias in the Workplace and Microbehaviours at Work modules (see ECI4). | No | Ongoing | Managers of Researchers | Annual OD audit on number of completions . A baseline from 2022, monitor and review completion rates yearly. |  | Those who participate in interviews are required to complete an online module. Interview panel members are reminded of this prior to participation. Completion rates for the recruitment and selection module: This has increased across the four years annually, and now completion is 2.5 x higher than in the initial 2019/20 year at 148 completions in 2022/23. Completion rates for Diversity in the Workplace module: This has increased across the four years annually, and now completion is 7 x higher than in the initial 2019/20 year at 118 completions in 2022/23. Completion rates for Unconscious Bias in the Workplace module: This has increased across the three years of availability, and now completion is 2 x higher than in the initial 2020/21 year at 101 completions in 2022/23. Completion rates for Microbehaviours module: This has increased across the three years of availability, and now completion is double that of the initial 2020/21 year at 101 completions in 2022/23. | The nature of the systems employed do not allow for an annual audit on number of completions by staff profile against total population. A breakdown of staff category (ie. research active staff) in completion data has previously provided a breakdown of Academic/Professional staff but this was through extensive manual checking. HR are investigating with the provider if academic/professional/research staff grouping can be automated to enhance reporting capabilities in relation to mandatory online learning. | carry forward
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | Contract of employment will inform HR related obligations. Regular policy brief spotlights will be included in Staff Roundup and Managers Network newsletters and included in the Researcher Guide. This will keep relevant institutional policies and guidance at the forefront. | No | Ongoing/Year spotlights/Year 2 Researcher Guide | Managers of Researchers/HR&OD | Inclusion in Managers Network newsletter ( 4 times p.a.) | REG subgroup for Researcher Guide is Dr Hannah Hale (REG lead), Dr Allison Ford (Co-lead) | The Manager's Network newsletter format is being reviewed. Awareness is being raised in HR Partner discussions. Can be included in the Researcher Guide under development year 2. | Included in new Researcher Guide. Policy updates provided as required through Roundup or HRP discussions with leadership teams. Managers Network being reshaped as part of leadership development offer. Communication around key HR related obligations/policy to be done through new manager's toolkit launching in 2024 | no further action - business as usual
ER1 | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder. | Information will be provided in employment contract. Visibility of institutional policies will also be raised via inclusion in Researcher Guide, regular Policy spotlights, web pages. | No | Ongoing | Researchers | n/a | REG subgroup for Researcher Guide is Dr Hannah Hale (REG lead), Dr Allison Ford (Co-lead) | REG lead for this subgroup is Research Fellow in FoSS, co-lead by non REG member Research Fellow, FHSS.Call for engagement Aug 2022 open to all with an interest.The Researcher Guide is a new information resource for PIs and new staff to naviagte policies, roles and expectations. Timeline of development activity was Oct 22- Feb 23 content drafting, FEB 7 REG meeting draft 1 shared for discussion, May shared with DP Research, REG, RIBE.and ADRs. June -July Graphics & Print, September October 2023 ready for Induction processes. | Included in new Researcher Guide. Awareness of the new guide will be monitored via CEDARS 2025, and internal fora. | no further action - business as usual
ER2 | Researchers understand their reporting obligations and responsibilities. | Contract of employment will inform HR related obligations. Grant funding will inform reporting responsibilties. Corporate, Faculty and local inductions as well as Researcher Guide will provide further information on wider roles and responsibilities. Clarification on role specific reporting obligations can be sought in AS/regular meetings with line manager. | No | Ongoing/Year 2 Researcher Guide | Researchers | n/a | REG subgroup for Researcher Guide is Dr Hannah Hale (REG lead), Dr Allison Ford (Co-lead) | REG lead for this subgroup is Research Fellow in FoSS, co-lead by non REG member Research Fellow, FHSS.Call for engagement Aug 2022 open to all with an interest.The Researcher Guide is a new information resource for PIs and new staff to naviagte policies, roles and expectations. Timeline of development activity was Oct 22- Feb 23 content drafting, FEB 7 REG meeting draft 1 shared for discussion, May shared with DP Research, REG, RIBE.and ADRs. June -July Graphics & Print, September October 2023 ready for Induction processes. | Included in new Researcher Guide. Awareness of the new guide will be monitored via CEDARS 2025, and internal fora. | no further action - business as usual
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | 4.1) Academic Leadership courses ILM3 (grades 6-8) and ILM 5 (grades 8-10) core part of Organistional Development offering. 4.2) IAS to offer tailored research focussed leadership and management courses as integral part of professional development programme. | No | Year 1 | HR&OD/IAS | Undertake an audit of course and programme completions in year 1 (2021/22) to use as a baseline metric for future review. Review in July 2022. |  | ILM/First Line Manager (FLM) course AY 2021/22 - 12 participants (11 academic and 1 P&S). Of the academic staff, 2 were research fellows. FLM was not delivered 2022/23 due to staff resourcing issues. Introduction of a new externally delivered Research Leadership Programme specifically aimed at research staff who lead research projects or will do in the near future. The programme has run 3 times since AY 2021/22 and is managed via an application process. | 54 research active staff from across all 5 Faculties have participated to date - 20 in the first cohort of Research Leadership Programme AY 2021/22. Feedback was very positive and the programme was subsequently run across both semesters AY 2022/23 where 34 participants took part in total. Post event surveys have an average star rating of 4.5/5 stars and a 100% recommend rate. There is no evaluation of ILM programmes available. There will be a review of all development offerings by HR in 2024/25, including leadership. | no further action - business as usual
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | 5.1) Annual Research Culture Awards which takes place during the Spring Festival of Research is an initiative to recognise and celebrate people and groups who contribute to a postive research environment and highlights traits not captured with traditional metrics. 5.2) Raise awareness of good research culture from award outcomes in Research Bites blog, report to University Research Committee and emails to Deans of Faculty. | No | Annual | Dean REP/IAS | 1) Increase in event engagement. +60 nominations made in inaugural awards 2020, +150 nominations in 2021. 2) post awards blog contribution to the Research Bites series | REG subgroup led by Prof Rachel Norman | 5.1.1 Research Culture Awards were held on 2 June 2023 and 27 May 2022 during the annual Festival of Research. The Research Awards have gained momentum with the number of people nominating increasing from 63 in 2020 to 165 in 2023 and the number of nominations increasing from 125 to 286. 5.1.2 A submission to the Concordat Platform of Practice was made in Nov 2022 to highlight the Research Culture Awards activity and the Awards initiative also features in the UUK 2022 annual report. 5.2 To raise the profile of Research Culture and share understanding across the institution a REG subgroup was created with support from RIBE staff. This initiative is two-fold: i) to set-up a Research Culture Network. 12 Research Champions from different career stages and faculties (October 2022), using the Research Culture Awards to identify good practice and foster a community of practice; ii) to develop monthly Research Culture Conversations series. | Research Culture Award nominations in 2022 were 243 and in 2023 were 286 (+15%). See ECI5 line 53 for Research Culture initiative info. | carry forward - BAU
|  | 5.3. Provide performance and people management training via i) the Achieving Success Conversations Programme suite of 7 standalone modules comprising Achieving Success for Reviewers, Achieving Success for Reviewees, Professional Excellence Framework, comprising Giving 360 feedback, Communicating Assertively, Giving and Receiving Feedback and Goal Setting for Performance.; ii) Coaching Conversations Programme comprising 3 standalone sessions on Workplace Coaching, the Coaching Mindset and Coaching Peer Practice. | No | Annual | HR&OD | Undertake an audit of course completions in year 1 (2021/22) to use as a base line metric for future review. Review in July 2022. |  | Course completion info for AY 2021/22 (max 12 capacity): Difficult conversations: 100% attendance rate , 31% attendance academic staff Achieving Success for Reviewers & Communicating Assertively : both 58% attendance rate. Achieving Success attendance was 100% professional services staff, while academic staff attendance at Communicating Assertively accounted for 29%. Goal Setting for performance: 42% attendance rate, 20% academic staff. Giving & Receiving Feedback: 16% attendance rate. All attendees were members of professional services. Not run AY 2022/23. | No longer run. TBC how these will be delivered as part of new strategic learning offer moving forward from 2023/24. Evaluations on courses not completed; therefore not able to measure but have identified there would be benefit in streamlining these into one cohesive and focussed programme. | completed - no further action
|  | 5.4. Creation of a dedicated Achieving Success form for career development conversations with contract researchers which reflects the timescales and paths of fixed term staff. | No | Year 1 | REG | Achieving Success form is created for 2022. Monitor increase via CEDARS 2023 against CEDARS 2021 baseline of 24.6% respondents having formal regular career development reviews (separately or as part of staff appraisal) and 33.3% of respondents strongly/agree they have a clear development plan. | REG subgroup | AS for fixed term staff created and tested by REG colleagues Year 1. Phase 2 plans were to create guidance and video resource on how to & why to use it with REG members ETA Jan 2023. On hold as of 22/12 pending discussion with HR on 16 Jan as review of AS pending | Achieving Success to be reviewed as part of a wider institutional review in late 2023/24. CEDARS 2023 showed an increase (+14.3%) in respondents having formal regular career development reviews in 2023 compared to baseline 2021 (38.9% V 24.6%). The 2023 responses also show an increase (+ 6%) in relation to having a clear development plan – 36.2% v 30.3% agreeing/agreeing strongly. | carry forward
|  | 5.5 Include guidance on Achieving Success conversations in the Researcher Guide | No | From Year 2 | HR & OD/REG | Monitor increase via CEDARS 2023 against CEDARS 2021 baseline of 24.6% respondents having formal regular career development reviews (as per of or separate to staff appraisal) and 33.3% of respondents strongly/agree they have a clear development plan. | REG subgroup for Researcher Guide is Dr Hannah Hale (REG lead), Dr Allison Ford (Co-lead) | AS for fixed term staff created and tested by REG colleagues during Aug 2022. Phase 2: to create guidance and video resource on how to & why to use it with REG members. ETA Jan 2023. On hold as of 22/12 pending discussion with HR on 16 Jan as review of AS pending. The purpose and timings of the Achieving Success conversation have been included in the new Researcher Guide resource. | Information on how to have Achieving Success conversations can be included in researcher guide at a later date. Achieving Success to be reviewed as part of a wider institutional review in late 2023/24. CEDARS 2023 showed an increase (+14.3%) in respondents having formal regular career development reviews in 2023 compared to baseline 2021 (38.9% V 24.6%). The 2023 responses also show an increase (+ 6%) in relation to having a clear development plan – 36.2% v 30.3% agreeing/agreeing strongly. | no further action - business as usual
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | Undertake Performance Conversations suite of training, Leadership and Achieving Success Reviewers training as appropriate (see EI4 & EI5). | No | Year 1 | Managers of Researchers/HR&OD | Undertake an audit of course completion in year 1 to use as a base line metric for future review. |  | *Refer to EI4 for research staff data on Leadership training (J89) : ILM/First Line Manager (FLM) course AY 2021/22 - 12 participants (11 academic and 1 P&S). Of the academic staff, 2 were research fellows. FLM was not delivered 2022/23 due to staff resourcing issues. Introduction of a new externally delivered Research Leadership Programme specifically aimed at research staff who lead research projects or will do in the near future. The programme has run 3 times since AY 2021/22 and is managed via an application process. | HR have provided Achieving Success training sessions for academic and research staff in FAH and FHSS in 2023. Sessions have included specific reference to research staff. No evalutation of these sessions was completed as they were short 'refreshers'. Recording made available at Faculty level for all staff to access. | completed - no further action
EM4 | Managers actively engage in regular constructive performance management with their researchers. | Undertake and record Achieving Success discussions, adopting and adapting the AS template form to needs (see EM1 for professional development training expectations). | No | Ongoing | Managers of Researchers/HR&OD | Undertake an audit of course completion in year 1 to use as a base line metric for future review. |  | *Refer to EI4 for research staff data on Leadership training (J89) : ILM/First Line Manager (FLM) course AY 2021/22 - 12 participants (11 academic and 1 P&S). Of the academic staff, 2 were research fellows. FLM was not delivered 2022/23 due to staff resourcing issues. Introduction of a new externally delivered Research Leadership Programme specifically aimed at research staff who lead research projects or will do in the near future. The programme has run 3 times since AY 2021/22 and is managed via an application process. | HR have provided Achieving Success training sessions for academic and research staff in FAH and FHSS in 2023. Sessions have included specific reference to research staff. No evalutation of these sessions was completed as they were short 'refreshers'. Recording made available at Faculty level for all staff to access. | completed - no further action
ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | Participate in Achieving Success conversations when invited to do so, detailing outcome of conversations and professional development undertaken/plans. Maintain a career development plan. | No | Ongoing | Researchers | CEDARS 2023 provides data on AS engagement and usefulness from research staff |  | Monitoring via CEDARS 2023. Responses re. having a regular career development review (37.5% in 2023). 70% in CEDARS 2023 stated that these reviews were useful. | From CEDARS 2023 130 staff engaged in AS and 62.3% found it useful/very useful. This is unvaried from CEDARS 2021. Over a third of respondents however did not find AS very useful and 43% have not participated as have not been invited to do so (-8.7% on 2021). | no further action - business as usual
Job security
The aim of this obligation is to improve the job security of researchers.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | Promote awareness of redeployment and pay protection policies via Researchers Guide and policy briefs in Round Up/Managers Network newsletters | No | Researchers Guide from Year 2 Policy briefs from Year 1 | HR&OD/CMR | Awareness will be monitored via CEDARS 2023. 16.3% of respondents in CEDARS 2021 strongly/agreed that redundancy processes were clear. | REG subgroup for Researcher Guide is Dr Hannah Hale (REG lead), Dr Allison Ford (Co-lead) | These policies continue to be promoted through discussions with Line Managers and HR Partners, specifically where they may be relevant to individuals. The HR Partnering team was back to full resource late 2022, with an HR Partner aligned to each of the five Faculties. HR Partners work with managers within their areas to provide guidance and support, and ensure managers are aware of relevant policies and procedures. Awareness is not being raised via Staff Roundup/Managers Network but has been included in the Researcher Guide. | CEDARS 2023 showed an unvaried awareness of redeployment processes in 2023 compared to baseline 2021 (16.8% V 16.3%) | completed -BAU
|  | Investigate the implications (financial and employment) of offering open ended contracts from 3 years with funding where possible | No | Year 2 | HR & OD | Undertake an audit of those on FTC of more than 3 years. Analyse and report on the financial and employment implications of offering open ended contracts from 3 years. No progress due to other priorities 21/3/2023 |  | This action has been reframed for the 2023-26 action plan, as a Contract Review Project. |  | carry forward
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | Embed 10 days within new drafting of Research Strategy and issue an institutional statement in support of commitment to provide such opportunities. Clearly communicate the expectation of min 10 days with examples of internal and external professional development opportunities to gain broader professional competencies (such as participation in mentoring schemes, committee membership, public engagement, knowledge exchange activities, as well as training workshops) via different channels (Research Bites Blog series, MS Teams Concordat channel, induction) and facilitate opportunities to undertake development. | No | From year 1 | DP Research/REG | Awareness of opportunities and positive increase in engagement will be monitored via CEDARS 2023. 56.7% of respondents to CEDARS 2021 have spent 0-2 days on professional development activities in the last 12 mths. | REG Subgroup lead Dr Susan Alexander (RIBE) | 10 days statement of intent created via REG working group. This action was delayed and work started in Year 2, with a statement of intent on 10 days development drafted by a subgroup and reviewed by REG. Currently with ADRs June 2023. This document will be launched via website, Staff Roundup, Research Culture Champions conversations and IAS Research Staff Canvas (intranet) in Dec 2023. | CEDARS 2023: The number of days spent on training and other continuing professional development activities is broadly the same as 2021, with 53.8% undertaking 0-2days. The number of respondents undertaking the recommended minimum 10 days prof development per year sits at 10.6% (down 0.4% from 2021). Small but positive fluctuations can be seen in the number of respondents who do less than 1 day CPD (-5%), 5% increase in 1-2days and 3% increase 5-9 days. | carry forward
|  | Review and monitor guidance from Research Councils on how to include professional development time in bids. | No | Year 1 Review Year 2 inclusion in Researcher Guide | REG/RIBE | Inclusion of guidance in Researchers Guide |  | A top level review of Concordat signatories to see approach for time & costs in funding was carried out in Year 1. As funder approaches vary greatly it was agreed in REG that this action would change to focus on institutional statement of intent and clarity around CPD expectations (see line 104). Costing of time for professional development within bids is part of the grant development discussion with RIBE RDOs. | Researcher Guide launched for AY 2023/24 and 10 days Professional Development guidelines under review - launch 2023/24. | completed - no further action
|  | Provide support for senior research colleagues to share learning and explore how to strengthen research teams and capacity build for future research generations. We will hold three University wide “Professorial Colloquia” that will bring professorial staff form across the University to share best practice, develop research teams, and build capacity of early career researchers. | Yes | From Year 1 | DEAN REP/REG | Three professorial research colloquia will be held 2021-2023. | REG subgroup led by REG Chair | Three professorial colloquia open to all research active staff were delivered. The first professorial colloquium (Leadership) was held during Festival on 27 May 2022 with 17 participants. The second professorial colloquium (Interdisciplinary Collaborations Uncovered) was held on 16 December 2022 with 37 participants. The third professorial colloquiuim (How to negotiate your academic journey - different pathways to survive and thrive) was held Fri 26 May 2023 with 16 participants. | 70 staff reached by the 3 Colloquia. 4.5 out of 5 star average satisfaction. | completed - no further action
|  | Promote engagement in the IAS Researcher Development Programme (RDP). The RDP is reviewed annually and the provision of workshops for professional and career skill building is designed with feedback from the researcher community, gathered via dedicated padlets/surveys, informal coffee mornings and CEDARS data. IAS runs a dedicated career management programme in collaboration with CES and Alumni teams. Alongside this, RIBE provides a dedicated Enterprise & Innovation development programme and HR&OD offer a suite of personal development opportunities, including the ILM programme. | No | Ongoing | IAS/HR&OD | Monitoring and reporting of Research Staff workshop attendance data and qualitative feedback. Awareness of opportunities and engagement will also be monitored via CEDARS. 75% of repondents to CEDARS 2021 were aware of the RDP, with 48.2% participating in the IAS programme. |  | The IAS- RDP 2022- 2023 comprised 29 staff focussed sessions (8 series and 5 standalone sessions), broadly in line with 2021-22, with new content delivered in the areas of research maagement, research leadership, writing & publishing and communication & impact. The IAS RDP 2021-23 also included 8 career development sessions, 6 of which were delivered in collaboration with CES. Research Staff engagement has been low overall in career focussed development sessions, with the highest attendance being at the Being Strategic in your Research Career session for postdocs (60% capacity). HR&OD ran two cohorts of ILM in 2020/21, with 11 academic staff attendees (including 2 Research Fellows). The Enterprise Programme see PCDR6 Line 137 | There was a 14% increase in staff engagement with the RDP over 2021-2023 compared to AY 2020/21. In terms of engagement by career stage, of the 138 individuals engaging (approx 25% of all research active staff), 76% were ECRs, 16% established and 8% senior researchers. Furthermore, CEDARS 2023 showed 82.8% awareness of opportunities for researcher development training offered by IAS ( +7.8% increase on baseline 2021); 72.2% of respondents had particpated in IAS sessions, a 24% increase on the CEDARS 2021 baseline. | no further action - business as usual
|  | Ensure Researcher Guide for new PIs and Researchers includes definition of professional development , clearly outlines expectation of 10 days and signposts available internal development opportunities. | No | From year 2 | REG | Awareness of opportunites and engagement will be monitored via CEDARS 2023 | REG subgroup for Researcher Guide is Dr Hannah Hale (REG lead), Dr Allison Ford (Co-lead) | 10 days statement of intent created via REG working group. This action was delayed, with a statement of intent on 10 days development drafted and under review by REG and ADRs in June 2023. This document will be launched via website, Staff Roundup, Research Culture Champions conversations and IAS Research Staff Canvas (intranet) in Dec 2023. | CEDARS 2023 showed just over 10% of respondents have not engaged in any form of training/CPD activities in the last year while 10% have engaged in 10 days or more. A third of respondents have spent 1-2 days on training and other CPD activities in the last 12mths. The remaining 63.8% have undertaken for the most part 3-4 days, followed by 5-9 days. The number of days spent on training and other continuing professional development activities is broadly the same as 2021, with approx a third of respondents (28.3%) undertaking 1-2 days. The number of respondents undertaking the recommended minimum 10 days prof development per year sits at 10.6% (down 0.4% from 2021). Small but positive fluctuations can be seen in the number of respondents who do less than 1 day CPD (-5%), 5% increase in 1-2 days and 3% increase 5-9 days. | no further action - business as usual
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | See PCDI3 regarding dedicated AS template for contract researchers. Deliver AS Reviewers Training to communicate expectations regarding conducting AS conversations and manage expectations |  | Year 2 | REG/HR & OD | CEDARS will allow for monitoring an increase in the number of appraisals held and quality of experience. 79.2% of CEDARS 2021 respondents had participated in a staff appraisal, with 61.1% finding this very/useful. 24.6% have regular career development reviews as part of appraisal, with 86.6% finding these very/useful. Data on engagement with in-house AS Reviewers training 2021/22 will allow for a baseline to be established |  | AS form activity on hold (see PCDI3): AS for fixed term staff created and tested by REG colleagues Year 1. Phase 2 plans were to create guidance and video resource on how to & why to use it with REG members ETA Jan 2023. On hold as of 22/12 pending discussion with HR on 16 Jan as review of AS pending Progress against engagement can also be seen under PCDI6 (1.4) which gives an overview of engagement with the IAS RDP programme. | CEDARS 2023 showed 75% had received staff appraisal in the past two years or since they started (-4%). 130 respondents had participated in a staff appraisal and 62.3% of those found it useful, whilst 37.7% did not. Of the 42 respondents that did not participate in a staff appraisal 42.9% (18) have not been invited to do so and 35.7% (15) had only just been appointed. | completed - no further action
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | Clearly communicate the expectation and support for engagement in professional development activities such as training/workshops/mentoring/committee membership/public engagement etc in local inductions, during AS conversations and regular meetings,discussing individual needs accordingly. | No | Year 1 | Managers of Researchers | See PCDI1: Awareness of opportunities and positive increase in engagement will be monitored via CEDARS 2023. 56.7% of respondents to CEDARS 2021 have spent 0-2 days on professional development activities in the last 12 mths. |  | REG subgroup are developing 10 days Research Development Guide to be releasd in 2023 | New 10 days guide final draft nearly complete for release in 2023 and publication via the usual channels of Staff Roundup etc. | carry forward
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | Familiarise themselves with available in-house development programmes, exploring external opportunities and engage as and where appropriate. | No | From Year 1 | Researchers | See PCDI1: Awareness of opportunities and positive increase in engagement will be monitored via CEDARS 2023. 56.7% of respondents to CEDARS 2021 have spent 0-2 days on professional development activities in the last 12 mths. |  | REG subgroup are developing 10 days Research Development Guide to be releasd in 2023 | New 10 days guide final draft nearly complete for release in 2023 and publication via the usual channels of Staff Roundup etc. | carry forward
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | Creation of a dedicated Achieving Success (AS) form for career development conversations with contract researchers which reflects the timescales and paths of fixed term staff. Pilot a dedicated AS Reviewers course for Managers of Researchers Clearly communicate expectation that career development reviews are an integral part of AS conversations by including this in the AS template form and in the Researchers Guide. | No | Actions 1 & 2 From Year 1 Action 3 From Year 2 | REG / HR&OD | Pilot AS Reviewers course November 2021, monitoring number of attendees and evaluation feedback. | REG subgroup | AS for fixed term staff created and tested by REG colleagues during Aug 2022. Phase 2: to create guidance and video resource on how to & why to use it with REG members ETA Jan 2023. Action paused to allow for alignment with HR priority actions. | on hold pending institutional AS review | carry forward
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews. | See PCDI2 dedicated AS template for contract researchers. Deliver AS Reviewers Training to communicate expectations regarding conducting AS conversations and manage expectations | No | Year 2 | REG / HR&OD | CEDARS will allow for monitoring an increase in the number of appraisals held and quality of experience. 79.2% of CEDARS 2021 respondents had participated in a staff appraisal, with 61.1% finding this very/useful. 24.6% have regular career development reviews as part of appraisal, with 86.6% finding these very/useful. Data on engagement with in-house AS Reviewers training 2021/22 will allow for a baseline to be established. |  | AS training for reviewers and reviewees has been provided to Faculties by HR on an ad-hoc basis as requested in 2022/23. No data gathered on attendance or evaluation. | CEDARS 2023 showed 75% had received staff appraisal in the past two years or since they started (-4%). 130 respondents had participated in a staff appraisal and 62.3% of those found it useful, whilst 37.7% did not. Of the 42 respondents that did not participate in a staff appraisal 42.9% (18) have not been invited to do so and 35.7% (15) had only just been appointed. | no further action - BAU
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually. | Engage in AS Reviewers Training, adopt and adapt the AS template form to needs, engage in career development reviews and document the outcome of conversations. | No | Ongoing (Reviews) Year 1 (Training ) | Managers of Researchers | See PCDI6 (line 115): CEDARS will allow for monitoring an increase in the number of appraisals held and quality of experience. 79.2% of CEDARS 2021 respondents had participated in a staff appraisal, with 61.1% finding this very/useful. 24.6% have regular career development reviews as part of appraisal, with 86.6% finding these very/useful. Data on engagement with in-house AS Reviewers training 2021/22 will allow for a baseline to be established. |  | AS training for reviewers and reviewees has been provided to Faculties by HR on an ad-hoc basis as requested in 2022/23. No data gathered on attendance or evaluation. | CEDARS 2023 showed 75% had received staff appraisal in the past two years or since they started (-4%). 130 respondents had participated in a staff appraisal and 62.3% of those found it useful, whilst 37.7% did not. Of the 42 respondents that did not participate in a staff appraisal 42.9% (18) have not been invited to do so and 35.7% (15) had only just been appointed. | no further action - BAU
PCDR4 | Researchers positively engage in career development reviews with their managers. | Career development reviews are an integral part of the AS conversation. Further career support can be provided by CES. | No | Ongoing | Researchers | See PCDI3 (lines 120 & 122)
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | Raise awareness that CES provides access to specialist career advice, also for research staff. CES has 4 career advisors (3 FT) aligned to Faculty. | No | Ongoing | CES | Monitor awareness of internal career support via insitution specific CEDARS question |  | *Researcher careers items added to IAS newsletter each month to promote CES, and also in weekly Staff RoundUp University newsletter * As of October 2022 CES will have 5 careers consultants, 3.8FTE. 4 Consultants aligned to each faculty, and one consultant dedicated . international students/ECRs. Impact will be measured in CEDARS 2023 and in research staff registrations in the RDP AY 2022/23. 5 career advisors (4 aligned to Faculty) | CEDARS 2023 showed a 15% decrease in staff who rated career support poor/very poor (from 34.2% in 2021 to 19.7% in 2023). | no further action - BAU
|  | See PCDI1 CES work in collaboration with IAS on a rolling basis to offer a Career Management series within the IAS development programme to raise awareness of alternative careers, with some complementary activity conducted at local level. The CES-IAS-Alumni Beyond Academia Panel and Networking event which brought speakers from across the world to virtually explore early career pathways outside of the HE sector was successfully piloted in June 2020. Continue to build on this event and expand researcher alumni network. | No | Annual | CES/IAS | Monitor increase in engagement via reporting of IAS workshop attendance data and qualitative feedback |  | CES/IAS ran a Beyond a PhD careers panel session exploring Professional Services careers for doctoral graduates within HEI in June 2022. While the session well received Research Staff engagement was very low (1 research staff member attending). The session has been recorded and available on IAS Canvas module. CES/IAS continued to develop more research focussed careers events AY 22/23 with 4 careers focussed events exploring "Interviewing skills" for ECRs and Online networking. | Low attendance (<10 in total) for events. Support from CES was rated 37% good/very good (+15% on 2021) and 43% fair (+20% ) in CEDARS 2023. | completed -BAU
|  | Development of a fixed term researchers AS template to guide career development conversations (see EI5 ) | No | Year 1 | HR&OD/REG | Achieving Success form is created for 2022. Monitor increase via CEDARS 2023 against CEDARS 2021 baseline of 24.6% respondents having formal regular career development reviews (as part of or separate to staff appraisal) and 33.3% of respondents strongly/agree they have a clear development plan. |  | Achieving Success template for contract researchers developed and piloted by a REG subgroup September 2022 with the planned release in Jan 2023 of a video resource available via IAS Canvas module highlighting how such a conversation can be conducted by a PI and a Research Fellow. The video action was paused pending a full review of AS by HR. | In CEDARS 2023 39% respondents have formal regular career development reviews (as part of or separate to staff appraisal). This is 14% increased compared to baseline in 2021. CEDARS 2023 responses show a slight increase (+ 3%) in relation to having a clear development plan agreeing/agreeing strongly. However, a third (+16%) of respondents who do have a regular formal career development review do not find it useful (very/at all). | carry forward
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | Record engagement in training and development opportunities and discuss in AS conversations | No | Ongoing | Researchers | Monitoring of development plans via CEDARS 2023 |  | UoS does not have a management platform/software for tracking development. The onus is therefore on individuals to keep track of their own training & development. | Over half of CEDARS 2023 respondents do not have a clear development plan (56.4%), down 7% on CEDARS 2021. | completed - no further action
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | Increase awareness of and promote participation in the University-wide Mentoring Scheme via Managers Network newsletter, IAS newsletter, via ECR MS Teams and Concordat channel and induction. | No | Year 1 | HR&OD | Monitor engagement via annual reporting on institutional mentoring links: Undertake an audit of scheme partnerships in year 1 (2021/22) as a baseline for future review. CEDARS 2023 will also allow for monitoring an increase in uptake in the number of informal/formal mentoring in place: CEDARS 2021 data shows that 39.6% of UoS respondents have a formal/informal mentor, with 40.2% acting as a formal/informal mentor. |  | It was not possible to audit the university-wide mentoring scheme. Mentoring processes at faculty/divisional level vary signficantly: FNS - there is no standard faculty approach, e.g. BES - a mentor is assigned to the new staff member from within the division, before induction and for an undefined period (as long as the mentee requires); IoA info pending; Psychology: a senior colleague is assigned as part of the probation scheme at induction usually for the duration of the probation period; CSM: a mentor from the division is assigned at induction normally indefintely; FAH: Deputy Dean working with colleagues in FSS to review and introduce a new and more robust scheme; FoSS: All probationers are assigned a senior colleague/mentor. For all others, as a matter of systemic approach, mentoring needs are assessed during Achieving Success conversations. Research mentoring needs in the past few years were specifically addressed via Research group rep at the AS meeting; there was also scope to pick up broader mentoring needs at the Res group meetings and interactions. | CEDARS 2023 showed that 23% have a formal mentor at Stirling, 26% have an informal mentor (+12% on CEDARS 2021). 19% act as a formal mentor and 31% as an informal mentor (+10%). 86% agree strongly or agree with the statement “I value mentoring”(unvaried) and 89% agree that they feel confident in their mentoring ability (+26%). Only 13% had had any formal mentoring training in the last 3 years (-3.5% on CEDARS 2021). | carry forward
|  | Explore participation in external mentoring scheme TRAM (Teaching, Research and Academic Mentoring Scheme) - 7-way collaboration with University of St Andrews/UoD/QMU/Abertay/Glasgow School of Art/James Hutton Institute/Trinity College Dublin (medicine) | No | From Year 2 | IAS | Review at REG September 2022 | Project Lead Claire Bradley | This action has been reframed for the 2023-26 action plan, with the introduction of a new mentoring scheme/platform |  | carry forward
|  | Continue to deliver the biennial Stirling Crucible, which is a development opportunity for ECRs to build research networks, and promote interdisciplinary collaborations. Stirling Crucible is a 2-phase initiative, with dedicated skills workshops and social activities in year 1, and research project development with seed funding in year 2. | No | Year 2 | IAS | Min 15 participants in each Stirling Crucible cohort from across all 5 Faculties, with an increase in positive evaluation feedback & project outcomes | Project Lead Claire Bradley | Applications for Stirling Crucible 2022/23 cohort closed November 2022. A panel review was conducted and outcomes ommunciated December 2022. Crucible 2023 had 3 two-day workshops held over 19 & 20 April, 10 & 11 May and 7 & 8 June. A co-creation approach is undertaken to developing this event with an organising team comprising 4 past academic Crucible participants (ECR) and RIBE colleagues. | Feedback from Crucible 2022/23 was very positive: 4.9 star rating and a 100% recommend rate (52% response rate, 17 participants in total taking part in Stirling Crucible series of events 2023). | no further action - business as usual
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours. | Discuss appropriate internal and external professional development opportunities and encourage participation (see PCDI1 & PCDI4). Highlight and support activities externally to develop research reputuation (networking, conferences, secondments etc). Recognition of efforts and contributions to be noted in AS reviews and discussed in Research Groups to share experiences and learning. | No | From Year 1 | Managers of Researchers | See PCDI1 & PCDI4 |  | 10 days statement of intent created via REG working group. This action was delayed and work started in Year 2, with a statement of intent on 10 days development drafted by a subgroup and reviewed by REG. Currently with ADRs June 2023. This document will be launched via website, Staff Roundup, Research Culture Champions conversations and IAS Research Staff Canvas (intranet) in Dec 2023. | Just over 10% of respondents have not engaged in any form of training/CPD activities in the last year while 10% have engaged in 10 days or more. A third of respondents have spent 1-2 days on training and other CPD activities in the last 12mths. The remaining 63.8% have undertaken for the most part 3-4 days, followed by 5-9 days. The number of days spent on training and other continuing professional development activities is broadly the same as 2021, with approx a third of respondents (28.3%) undertaking 1-2 days. The number of respondents undertaking the recommended minimum 10 days prof development per year sits at 10.6% (down 0.4% from 2021). Small but positive fluctuations can be seen in the number of respondents who do less than 1 day CPD (-5%), 5% increase in 1-2 days and 3% increase 5-9 days. | carry forward
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | Participate in HR & OD in-house ILM provision (ILM 3 & ILM 5). IAS to identify and include a dedicated Research Leadership and Management Programme for research leaders within development provision for 2021/22 | No | From Year 1 | Managers of researchers/HR&OD/IAS | See PCDI1: Awareness of opportunities and positive increase in engagement will be monitored via CEDARS 2023. 56.7% of respondents to CEDARS 2021 have spent 0-2 days on professional development activities in the last 12 mths. |  | ILM/First Line Manager (FLM) course AY 2021/22 - 12 participants (11 academic and 1 P&S). Of the academic staff, 2 were research fellows. There is no evaluation of ILM programmes available. FLM was not delivered 2022/23 due to staff resourcing issues. Introduction of a new externally delivered Research Leadership Programme specifically aimed at research staff who lead research projects or will do in the near future. The programme has run 3 times since AY 2021/22 and is managed via an application process. | 54 research active staff from across all 5 Faculties have participated to date - 20 in the first cohort of Research Leadership Programme AY 2021/22. Feedback was very positive and the programme was subsequently run across both semesters AY 2022/23 where 34 participants took part in total. Post event surveys have an average star rating of 4.5/5 stars and a 100% recommend rate. | no further action - business as usual
PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills | Actively engage in activities such as conference presentations/organisation, networking, grant proposal writing, publishing and secondments. Discuss opportunities and competencies gained in AS conversations. | No | Ongoing | Researchers | Monitor engagement via CEDARS 2023 |  | Monitoring via CEDARS 2023. The new Guidelines for the 10 days professional development have been produced and will be launched to all staff with research in contracts in 2023 (timing TBC). | Over half of CEDARS 2023 respondents stated they do not have time to develop their research identity (54%, -3% on 2021). Just under half of respondents (49%) do not have time to develop their leadership skills. There has however been a significant increase in training undertaken in many areas, including Research Leadership 2023 on 2021 (+19%). | carry forward
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | See PCDI3 CES & IAS activity: Raise awareness that CES provides access to specialist career advice, also for research staff. CES has 4 career advisors (3 FT) aligned to Faculty. CES work in collaboration with IAS on a rolling basis to offer a Career Management series within the IAS development programme to raise awareness of alternative careers, with some complementary activity conducted at local level. The CES-IAS-Alumni Beyond Academia Panel and Networking event which brought speakers from across the world to virtually explore early career pathways outside of the HE sector was successfully piloted in June 2020. Continue to build on this event and expand researcher alumni network. | No | Annual | CES/IAS |  |  | CES/IAS ran a Beyond a PhD careers panel session exploring Professional Services careers for doctoral graduates within HEI in June 2022. While the session well received Research Staff engagement was very low (1 research staff member attending). The session has been recorded and available on IAS Canvas module. CES/IAS continued to develop more research focussed careers events AY 22/23 with 4 careers focussed events exploring "Interviewing skills" for ECRs and Online networking. | Low attendance (<10 in total) for events. Support from CES was rated 37% good/very good (+15% on 2021) and 43% fair (+20% ) in CEDARS 2023. | no further action - business as usual
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | Engage in the University-wide mentoring scheme as mentor and encourage participation as appropriate, signpost CES & Alumni related activity and in-house IAS & OD development programmes. Highlight external opportunities for mentoring and career advice via professional/disciplinary bodies. | No | Ongoing | Managers of Researchers | See PCDI1, PCDI3 & PCDI4 |  | It is not possible to conduct an audit of the Uni-wide scheme. This is an informal scheme. Research staff are paired with a mentor on commencing and can request a mentor also via the Uni-wide mentoring scheme. Mentoring processes at faculty/divisional level vary signficantly: FNS - there is no standard faculty approach, e.g. BES - a mentor is assigned to the new staff member from within the division, before induction and for an undefined period (as long as the mentee requires); IoA info pending; Psychology: a senior colleague is assigned as part of the probation scheme at induction usually for the duration of the probation period; CSM: a mentor from the division is assigned at induction normally indefintely; FAH: Deputy Dean working with colleagues in FSS to review and introduce a new and more robust scheme; FoSS: All probationers are assigned a senior colleague/mentor. For all others, as a matter of systemic approach, mentoring needs are assessed during Achieving Success conversations. Research mentoring needs in the past few years were specifically addressed via Research group rep at the AS meeting. |  | carry forward
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | Consider engagement in appropriate internal activities such as participation in the University-wide Mentoring Scheme as mentee/mentor, HR & OD development opportunities, RIBE, CES & Alumni programme of training and events. Explore external opportunities for career development via professional /disciplinary bodies. | No | From Year 1 | Researchers | See PCDI1, PCDI3 & PCDI4 |  | It is not possible to conduct an audit of the Uni-wide scheme. This is an informal scheme. Research staff are paired with a mentor on commencing and can request a mentor also via the Uni-wide mentoring scheme. Mentoring processes at faculty/divisional level vary signficantly: FNS - there is no standard faculty approach, e.g. BES - a mentor is assigned to the new staff member from within the division, before induction and for an undefined period (as long as the mentee requires); IoA info pending; Psychology: a senior colleague is assigned as part of the probation scheme at induction usually for the duration of the probation period; CSM: a mentor from the division is assigned at induction normally indefintely; FAH: Deputy Dean working with colleagues in FSS to review and introduce a new and more robust scheme; FoSS: All probationers are assigned a senior colleague/mentor. For all others, as a matter of systemic approach, mentoring needs are assessed during Achieving Success conversations. Research mentoring needs in the past few years were specifically addressed via Research group rep at the AS meeting. |  | carry forward
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation. | Engagement with the Innovation and Enterprise (RIBE) programme of workshops, events and resources. | No | From Year 1 | Researchers | Monitoring can be captured via reporting on uptake of Innovation & Enterprise initiatives as well as supported via data from CEDARS 2023. |  | The Enterprise Programme is the University of Stirling's cross-institutional entrepreneurial training and business creation service. It offers a range of support, including training workshops, inspirational and educational events, individual access to business guidance and professional services (e.g., legal, financial and marketing advice), support with applications to external start-up / research commercialisation competitions, and an incubation offering and community on campus. The programme formally opened its services to staff members in 2021 with 5 individuals benefiting from access to individual business advisory support, 12 individuals attending workshops, and 2 individuals receiving assistance in submitting applications to external competitions (these figures may also include PGRs, attendance info AY 22/23 will capture Research Staff only to monitor engagement). Over AY2022/23: 7 staff colleagues benefited from access to 1-2-1 business advisory support, 9 research colleagues attended internal workshops, 11 research colleagues attended partner-led workshops, and 2 received 1-2-1 assistance in submitting applications to external competitions, one of which has been successful. Over Sept 2022-Auguest 2023 BEDT has grown substantially to support the University of Stirling’s engagement with businesses regionally, nationally, and internationally. The team has grown from a team of two, to a team of seven, with one final post yet to be recruited. Towards the end of 2022 BEDT submitted a bid to Innovate UK KTNs KTP Capacity Funding competition and were successfully awarded over £20,000. Part of this fund is dedicated to activity to raise awareness of the KTP opportunity to businesses in the Forth Valley Region. This has allowed engagement with local businesses to start creating a pipeline of KTP opportunity, with 6 KTP opportunities currently being supported for submission (July 2023). This compares to a total of 5 successful KTPs held over the last 6 years. | Increase in uptake of I&E initiatives (both 1-2-1 support and workshop attendance) in 2022-23. CEDARS 2023 showed that 33% consider support for commercialisation good- very good and 46% fair compared to 11.6% good/very good and 12.8% fair in 2021. The opportunity to collaborate externally with business/industry at Stirling has increased by 10% (CEDARS 2023). Furthermore it is noted that approx 30% of respondents have an interest in engaging in commercialisation and approx 40% in KE and PE. | no further action - business as usual
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | ECI3.2 (https://www.stir.ac.uk/about/professional-services/human-resources-and-organisation-development/working-at-stirling/staff-mental-health-and-wellbeing/occupational-health/)
2 | EI5 https://concordatplatformofpractice.vitae.ac.uk/case-studies/research-culture-awards |  |  |  | AAPC | Academic Advancement and Promotions Committee
3 | EI5 https://researcherdevelopmentconcordat.ac.uk/researcher-development-concordat-strategy-group-publishes-2022-annual-report/ |  |  |  | ADR | Associate Dean for Research
4 | ECR5 https://www.stir.ac.uk/research/festival-of-research/ |  |  |  | AS | Achieving Success - annual appraisal/review for staff
5 | ECR 5 https://www.stir.ac.uk/research/research-culture/research-culture-champions-network/ |  |  |  | BES | Biological and Environmental Sciences (Faculty of Natural Sciences)
[5 empty] | BEDT | Business Engagement and Development team
6 |  |  |  |  | CEDARS | Culture, Employment and Development in Academic Research Survey
7 |  |  |  |  | CES | Careers and Employablity Service
8 |  |  |  |  | CSM | Computing Statistics and Mathematics
9 |  |  |  |  | Dean EDI | Dean for Equality, Diversity and Inclusion
10 |  |  |  |  | DEAN REP | Dean of Research Engagement and Performance
11 |  |  |  |  | DP Research | Deputy Principal for Research
12 |  |  |  |  | ECR | Early career researcher (UoS definition in Comments box)
13 |  |  |  |  | FAH | Faculty of Arts & Humanities
14 |  |  |  |  | FHSS | Faculty of Health Sciences & Sport
15 |  |  |  |  | FNS | Faculty of Natural Sciences
16 |  |  |  |  | FoSS | Faculty of Social Sciences
17 |  |  |  |  | HR & OD | Human Resources and Organisation Development
18 |  |  |  |  | IAS | Institute for Advanced Studies
[5 empty] | IOA | Institute of Aquaculture (Faculty of Natural Sciences)
[5 empty] | KE | Knowledge Exchange
19 |  |  |  |  | OD | Organisation Development (part of HR)
[5 empty] | PE | Public Engagement
[5 empty] | PI | Principal Investigator
[5 empty] | RDF | Researcher Development Framework
[5 empty] | RDP | Researcher Development Programme
[5 empty] | REG | Research Environment Group
[5 empty] | RIBE | Research, Innovation and Business Engagment
[5 empty] | SMS | Stirling Management School
[5 empty] | UoS | University of Stirling
[5 empty] | URC | University Research Committee
[5 empty] | USPG | University Strategy and Policy Group